## Status Report
Status Report for Team 4 - League Manager
Project |  | Status: (Red/Yellow/Green)
Date: | 2024-01-18 | Overall Status: | Green
Contact: | Usman Farooqi | Explanation: | On schedule, no blockers
Prepared By: | Team 4
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes | [5 empty] | Questions/planning to complete
Usman | Player |  |  |  |  | team object contain players and courses?
Ariq | Coach | [5 empty] | include a list of players and coaches in the team object
Fuming | Team |  |  |  |  | how to handle errors? current method is set certain fields to say "not found" if error encountered
all errors will be pop ups
encoded in data layer by changing the "name" field(s) of the object
ID # | Key Issues | Action Plan |  |  | Status
1 | Database setup with data | Set up tables for own database |  |  | completed
2 | Entity Class (setup data model) | Create the classes for the entities |  |  | completed | constrants/business logic
3 | 1 method, 1 test | Code one working method and one working test |  |  | completed |  | names alpha and hyphens only, length < 250
4 | Dao coded | Implement the methods for the database dao |  |  | completed |  | wins + losses <= 82
5 | Dao tested | Test dao functionality |  |  | completed |  | team id must be valid when referenced by player or coach
6 | service coded | Implement methods for the service |  |  | completed |  | salary < 19 digits
7 | service tested | Test service functionality: positive and negative tests |  |  | in-progress |  | no duplicate team names
8 | controller coded | Implement methods for controller |  |  | in-progress
9 | front end - homepage | Create the "index" homepage |  |  | in-progress
10 | front end - table pages | Create the table pages for the front end (thymeleaf) |  |  | in-progress | stretch goals
11 | Finalize project | Add any documentation, clean up code, commit all work |  |  |  |  | ensure state is an actual state
drop down
Critical Milestones |  | Health | Due Date | Comment/Status
Environment setup |  | 100% |  | Finished |  | final todo
Back-end |  | 100% | 2024-01-22 | Finished |  |  | main page/error page
Business logic |  | 100% | 2024-01-22 | Finished |  |  | add data for sql
Front-end |  | 90% | 2024-01-23 |  |  |  | navigation
Testing |  | 100% | 2024-01-23 | Finished
Presentation |  | 90% | 2024-01-24
Reviewing requirements |  | 100% | 2024-01-22 | Finished
presentation: everything high level < 10 slides
intro
tech stack
why this project/problem being solved
erd
demo
lessons learned